## Feature Requirements
Feature ID | Phase | Module | Category | Feature Group | Feature Name | Priority | Status | Assignee | Est. Hours | Actual Hours | Start Date | Due Date | Completion Date | Notes | Blockers | Dependencies | Acceptance Criteria | Test Status
FR-0001 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | Username/password authentication | Critical | Not Started
FR-0002 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | Session management with JWT | Critical | Not Started
FR-0003 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | "Remember me" functionality | Critical | Not Started
FR-0004 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | Password reset workflow | Critical | Not Started
FR-0005 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | Account lockout protection | Critical | Not Started
FR-0006 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | Login System | Browser compatibility (Chrome recommended) | Critical | Not Started
FR-0007 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | User list with pagination (5000+ users support) | Critical | Not Started
FR-0008 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | Add/Edit user forms with validation | Critical | Not Started
FR-0009 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | User status management (Enable/Disable/Delete) | Critical | Not Started
FR-0010 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | Bulk user operations | Critical | Not Started
FR-0011 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | User search and filtering | Critical | Not Started
FR-0012 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | User Authentication System | User Management Interface | User activity logging | Critical | Not Started
FR-0013 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Role Management System | Role creation/editing interface | Critical | Not Started
FR-0014 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Role Management System | Granular permission assignment (page-level + function-level) | Critical | Not Started
FR-0015 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Role Management System | Role templates for common use cases | Critical | Not Started
FR-0016 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Role Management System | Role hierarchy support | Critical | Not Started
FR-0017 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Role Management System | Role assignment audit trail | Critical | Not Started
FR-0018 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Permission Engine | Real-time permission checking | Critical | Not Started
FR-0019 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Permission Engine | Dynamic UI based on permissions | Critical | Not Started
FR-0020 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Permission Engine | API endpoint security | Critical | Not Started
FR-0021 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Permission Engine | Permission inheritance logic | Critical | Not Started
FR-0022 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Role-Based Access Control (RBAC) | Permission Engine | Emergency admin access | Critical | Not Started
FR-0023 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Scope Configuration | Project scope assignment | Critical | Not Started
FR-0024 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Scope Configuration | Device group scope management | Critical | Not Started
FR-0025 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Scope Configuration | Product category restrictions | Critical | Not Started
FR-0026 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Scope Configuration | Hierarchical scope inheritance | Critical | Not Started
FR-0027 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Scope Configuration | Scope conflict resolution | Critical | Not Started
FR-0028 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Organization Management | Company logo upload and display | Critical | Not Started
FR-0029 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Organization Management | Organization profile management | Critical | Not Started
FR-0030 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Organization Management | Branding customization | Critical | Not Started
FR-0031 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Organization Management | Multi-tenant isolation | Critical | Not Started
FR-0032 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Management Scope System | Organization Management | Tenant admin capabilities | Critical | Not Started
FR-0033 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Time Zone Management | Critical Time Zone Features | Time zone selection interface (My Account > Preferences) | Critical | Not Started
FR-0034 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Time Zone Management | Critical Time Zone Features | Global time zone impact on all rules | Critical | Not Started
FR-0035 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Time Zone Management | Critical Time Zone Features | Device time synchronization | Critical | Not Started
FR-0036 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Time Zone Management | Critical Time Zone Features | Time zone change impact assessment | Critical | Not Started
FR-0037 | Phase 1: Core Infrastructure | Phase 1: Authentication & User Management | Time Zone Management | Critical Time Zone Features | UTC conversion for storage | Critical | Not Started
FR-0038 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Smart Gateway configuration | Critical | Not Started
FR-0039 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Smart Light Controller (Zigbee, LoRa, NB-IoT, CAT.1) | Critical | Not Started
FR-0040 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Lighting Fixture management | Critical | Not Started
FR-0041 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Lighting Pole organization | Critical | Not Started
FR-0042 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Power Distribution Control | Critical | Not Started
FR-0043 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Loop Control (Built-in + Extended) | Critical | Not Started
FR-0044 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | 7 Device Category Support | Smart Meter (485 three-phase) | Critical | Not Started
FR-0045 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | Device Configuration Interface | Device-specific configuration forms | Critical | Not Started
FR-0046 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | Device Configuration Interface | Mandatory field validation | Critical | Not Started
FR-0047 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | Device Configuration Interface | Device association workflows | Critical | Not Started
FR-0048 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | Device Configuration Interface | Coordinate management (lat/long) | Critical | Not Started
FR-0049 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Registration System | Device Configuration Interface | Project and group assignment | Critical | Not Started
FR-0050 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Critical Associations | Light Controller ↔ Lighting Fixture (critical for control) | Critical | Not Started
FR-0051 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Critical Associations | Sub-devices ↔ Gateway (required for communication) | Critical | Not Started
FR-0052 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Critical Associations | Device ↔ Project (security requirement) | Critical | Not Started
FR-0053 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Critical Associations | Device ↔ Group (organizational requirement) | Critical | Not Started
FR-0054 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Critical Associations | Association validation and warnings | Critical | Not Started
FR-0055 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Device Status Monitoring | Real-time online/offline status | Critical | Not Started
FR-0056 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Device Status Monitoring | Device communication health | Critical | Not Started
FR-0057 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Device Status Monitoring | Status indicator system (exclamation marks, symbols) | Critical | Not Started
FR-0058 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Device Status Monitoring | Connection quality metrics | Critical | Not Started
FR-0059 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Device Relationship Management | Device Status Monitoring | Last seen timestamps | Critical | Not Started
FR-0060 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Template system (device-specific templates) | Critical | Not Started
FR-0061 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Batch import (5000 device limit) | Critical | Not Started
FR-0062 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Data validation during import | Critical | Not Started
FR-0063 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Import error reporting and recovery | Critical | Not Started
FR-0064 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Export filtered device data | Critical | Not Started
FR-0065 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Progress tracking for large operations | Critical | Not Started
FR-0066 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Device deletion with binding checks | Critical | Not Started
FR-0067 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Recycle bin system with recovery | Critical | Not Started
FR-0068 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Device relationship cleanup | Critical | Not Started
FR-0069 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Historical data handling | Critical | Not Started
FR-0070 | Phase 1: Core Infrastructure | Phase 1: Device Management Core | Batch Operations | Import/Export System | Bulk device operations | Critical | Not Started
FR-0071 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Configuration Interface | Visual rule builder | Critical | Not Started
FR-0072 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Configuration Interface | Multi-condition support (AND/OR logic) | Critical | Not Started
FR-0073 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Configuration Interface | Trigger condition types (Attribute, Time, Range, Status) | Critical | Not Started
FR-0074 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Configuration Interface | Action configuration (Service, Lamp Control, Loop Control) | Critical | Not Started
FR-0075 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Configuration Interface | Device selection (individual + group selection) | Critical | Not Started
FR-0076 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Execution Engine | Real-time rule processing | Critical | Not Started
FR-0077 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Execution Engine | Rule scheduling system | Critical | Not Started
FR-0078 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Execution Engine | Condition evaluation logic | Critical | Not Started
FR-0079 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Execution Engine | Action execution queue | Critical | Not Started
FR-0080 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Platform Rules Foundation | Rule Execution Engine | Rule execution logging | Critical | Not Started
FR-0081 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Local Rule Management | Simple rule configuration (1 condition + 1 action) | Critical | Not Started
FR-0082 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Local Rule Management | Device synchronization system | Critical | Not Started
FR-0083 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Local Rule Management | Sync status tracking and retry | Critical | Not Started
FR-0084 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Local Rule Management | Local rule validation | Critical | Not Started
FR-0085 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Local Rule Management | Rule conflict detection | Critical | Not Started
FR-0086 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Synchronization Framework | Rule deployment to devices | Critical | Not Started
FR-0087 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Synchronization Framework | Sync success/failure reporting | Critical | Not Started
FR-0088 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Synchronization Framework | Bulk sync operations | Critical | Not Started
FR-0089 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Synchronization Framework | Manual retry mechanisms | Critical | Not Started
FR-0090 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Local Rules System | Synchronization Framework | Sync status dashboard | Critical | Not Started
FR-0091 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Platform Alarms | Alarm rule configuration | Critical | Not Started
FR-0092 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Platform Alarms | Multi-condition alarm triggers | Critical | Not Started
FR-0093 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Platform Alarms | Alarm level management | Critical | Not Started
FR-0094 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Platform Alarms | Notification system integration | Critical | Not Started
FR-0095 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Platform Alarms | Alarm status tracking | Critical | Not Started
FR-0096 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Offline/Device Alarms | Offline detection system | Critical | Not Started
FR-0097 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Offline/Device Alarms | Device event processing | Critical | Not Started
FR-0098 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Offline/Device Alarms | Automatic alarm handling | Critical | Not Started
FR-0099 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Offline/Device Alarms | Silent period management | Critical | Not Started
FR-0100 | Phase 1: Core Infrastructure | Phase 1: Basic Rule Engine | Basic Alarm System | Offline/Device Alarms | Alarm escalation workflows | Critical | Not Started
FR-0101 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Statistical Overview | Device count summaries | Critical | Not Started
FR-0102 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Statistical Overview | Status distribution charts | Critical | Not Started
FR-0103 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Statistical Overview | Project-based data filtering | Critical | Not Started
FR-0104 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Statistical Overview | Real-time data updates | Critical | Not Started
FR-0105 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Statistical Overview | Configurable dashboard modules (8 max) | Critical | Not Started
FR-0106 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Device Lists | Paginated device lists with search | Critical | Not Started
FR-0107 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Device Lists | Column customization | Critical | Not Started
FR-0108 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Device Lists | Device filtering by type/status/project | Critical | Not Started
FR-0109 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Device Lists | Device sorting capabilities | Critical | Not Started
FR-0110 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Homepage Dashboard | Device Lists | Quick actions (view, edit, control) | Critical | Not Started
FR-0111 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Individual Device Control | Device detail pages (6 major sections) | Critical | Not Started
FR-0112 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Individual Device Control | Real-time status display | Critical | Not Started
FR-0113 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Individual Device Control | Manual device commands | Critical | Not Started
FR-0114 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Individual Device Control | Historical data viewing | Critical | Not Started
FR-0115 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Individual Device Control | Device rule management | Critical | Not Started
FR-0116 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Basic Group Operations | Group-level device control | Critical | Not Started
FR-0117 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Basic Group Operations | Bulk status updates | Critical | Not Started
FR-0118 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Basic Group Operations | Group configuration management | Critical | Not Started
FR-0119 | Phase 1: Core Infrastructure | Phase 1: Basic Dashboard | Basic Device Control | Basic Group Operations | Group performance monitoring | Critical | Not Started
FR-0120 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Interactive map with device positioning | High | Not Started
FR-0121 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Device distribution workflow | High | Not Started
FR-0122 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Single device positioning (double-click) | High | Not Started
FR-0123 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Batch device positioning (path drawing) | High | Not Started
FR-0124 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Coordinate fine-tuning | High | Not Started
FR-0125 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | GIS Map Interface | Map search and navigation | High | Not Started
FR-0126 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | Device Visualization | Category-specific device icons | High | Not Started
FR-0127 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | Device Visualization | Status-based icon colors | High | Not Started
FR-0128 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | Device Visualization | Device clustering for performance | High | Not Started
FR-0129 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | Device Visualization | Info popups on device click | High | Not Started
FR-0130 | Phase 2: Advanced Features | Phase 2: GIS Integration | Map Integration | Device Visualization | Map-based device filtering | High | Not Started
FR-0131 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Coordinate Management | Lat/long coordinate storage | High | Not Started
FR-0132 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Coordinate Management | Address geocoding | High | Not Started
FR-0133 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Coordinate Management | Bulk coordinate operations | High | Not Started
FR-0134 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Coordinate Management | Coordinate validation | High | Not Started
FR-0135 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Coordinate Management | Import coordinates from files | High | Not Started
FR-0136 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Sunrise/Sunset Calculations | Location-based time calculations | High | Not Started
FR-0137 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Sunrise/Sunset Calculations | Daily automatic updates | High | Not Started
FR-0138 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Sunrise/Sunset Calculations | Time zone integration | High | Not Started
FR-0139 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Sunrise/Sunset Calculations | Seasonal adjustment | High | Not Started
FR-0140 | Phase 2: Advanced Features | Phase 2: GIS Integration | Location-Based Features | Sunrise/Sunset Calculations | Rule integration for lighting | High | Not Started
FR-0141 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Advanced Conditions | Multi-device conditions | High | Not Started
FR-0142 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Advanced Conditions | Complex time ranges | High | Not Started
FR-0143 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Advanced Conditions | Weather integration (optional) | High | Not Started
FR-0144 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Advanced Conditions | Sensor threshold combinations | High | Not Started
FR-0145 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Advanced Conditions | Historical data triggers | High | Not Started
FR-0146 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Rule Templates | Common rule patterns | High | Not Started
FR-0147 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Rule Templates | Rule templates library | High | Not Started
FR-0148 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Rule Templates | Template customization | High | Not Started
FR-0149 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Rule Templates | Best practice examples | High | Not Started
FR-0150 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Complex Rule Logic | Rule Templates | Rule sharing between projects | High | Not Started
FR-0151 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Comprehensive Alarm Processing | Multi-dimensional alarm filtering | High | Not Started
FR-0152 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Comprehensive Alarm Processing | Alarm workflow management | High | Not Started
FR-0153 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Comprehensive Alarm Processing | Escalation procedures | High | Not Started
FR-0154 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Comprehensive Alarm Processing | Automatic alarm handling | High | Not Started
FR-0155 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Comprehensive Alarm Processing | Alarm analytics and trends | High | Not Started
FR-0156 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Notification System | Multiple notification channels (Email, SMS, Push) | High | Not Started
FR-0157 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Notification System | Receiving group management | High | Not Started
FR-0158 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Notification System | Notification scheduling | High | Not Started
FR-0159 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Notification System | Notification rate limiting | High | Not Started
FR-0160 | Phase 2: Advanced Features | Phase 2: Advanced Rule Engine | Enhanced Alarm System | Notification System | Delivery confirmation | High | Not Started
FR-0161 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Live Monitoring | WebSocket integration for real-time updates | High | Not Started
FR-0162 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Live Monitoring | Live device status changes | High | Not Started
FR-0163 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Live Monitoring | Real-time alarm notifications | High | Not Started
FR-0164 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Live Monitoring | Dynamic chart updates | High | Not Started
FR-0165 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Live Monitoring | Connection status monitoring | High | Not Started
FR-0166 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Advanced Visualizations | Time-series charts | High | Not Started
FR-0167 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Advanced Visualizations | Energy consumption graphs | High | Not Started
FR-0168 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Advanced Visualizations | Device performance metrics | High | Not Started
FR-0169 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Advanced Visualizations | Trend analysis | High | Not Started
FR-0170 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Real-Time Features | Advanced Visualizations | Custom chart configurations | High | Not Started
FR-0171 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | GIS-Based Control | Map-based device operations | High | Not Started
FR-0172 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | GIS-Based Control | Group control from map | High | Not Started
FR-0173 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | GIS-Based Control | Batch operations via map selection | High | Not Started
FR-0174 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | GIS-Based Control | Visual feedback for operations | High | Not Started
FR-0175 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | GIS-Based Control | Operation history tracking | High | Not Started
FR-0176 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | Advanced Device Management | Device maintenance workflows | High | Not Started
FR-0177 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | Advanced Device Management | Performance optimization tools | High | Not Started
FR-0178 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | Advanced Device Management | Predictive maintenance alerts | High | Not Started
FR-0179 | Phase 2: Advanced Features | Phase 2: Advanced Dashboard | Operation Control Interface | Advanced Device Management | Device lifecycle tracking | High | Not Started
FR-0180 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Data Analytics Dashboard | Energy consumption analysis | Medium | Not Started
FR-0181 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Data Analytics Dashboard | Device performance trends | Medium | Not Started
FR-0182 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Data Analytics Dashboard | Usage pattern identification | Medium | Not Started
FR-0183 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Data Analytics Dashboard | Cost analysis | Medium | Not Started
FR-0184 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Data Analytics Dashboard | Environmental impact metrics | Medium | Not Started
FR-0185 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Report Generation | Automated report scheduling | Medium | Not Started
FR-0186 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Report Generation | Custom report builder | Medium | Not Started
FR-0187 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Report Generation | Multiple export formats | Medium | Not Started
FR-0188 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Report Generation | Report template system | Medium | Not Started
FR-0189 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Statistical Analysis | Report Generation | Data visualization options | Medium | Not Started
FR-0190 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | KPI Monitoring | Energy savings calculations | Medium | Not Started
FR-0191 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | KPI Monitoring | System uptime tracking | Medium | Not Started
FR-0192 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | KPI Monitoring | Maintenance efficiency | Medium | Not Started
FR-0193 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | KPI Monitoring | Cost optimization metrics | Medium | Not Started
FR-0194 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | KPI Monitoring | ROI analysis | Medium | Not Started
FR-0195 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | Predictive Analytics | Device failure prediction | Medium | Not Started
FR-0196 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | Predictive Analytics | Energy demand forecasting | Medium | Not Started
FR-0197 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | Predictive Analytics | Maintenance scheduling optimization | Medium | Not Started
FR-0198 | Phase 3: Analytics & Optimization | Phase 3: Analytics & Reporting | Business Intelligence | Predictive Analytics | Performance degradation alerts | Medium | Not Started
FR-0199 | Cross-Phase | Performance & Optimization | System Performance | Scalability Requirements | Support 5000+ devices per batch operation | Standard | Not Started
FR-0200 | Cross-Phase | Performance & Optimization | System Performance | Scalability Requirements | Handle 1000+ concurrent users | Standard | Not Started
FR-0201 | Cross-Phase | Performance & Optimization | System Performance | Scalability Requirements | Real-time updates for 10,000+ devices | Standard | Not Started
FR-0202 | Cross-Phase | Performance & Optimization | System Performance | Scalability Requirements | Sub-second response times for critical operations | Standard | Not Started
FR-0203 | Cross-Phase | Performance & Optimization | System Performance | Scalability Requirements | Efficient database queries for large datasets | Standard | Not Started
FR-0204 | Cross-Phase | Performance & Optimization | System Performance | Optimization Features | Caching system for frequently accessed data | Standard | Not Started
FR-0205 | Cross-Phase | Performance & Optimization | System Performance | Optimization Features | Background processing for heavy operations | Standard | Not Started
FR-0206 | Cross-Phase | Performance & Optimization | System Performance | Optimization Features | Database query optimization | Standard | Not Started
FR-0207 | Cross-Phase | Performance & Optimization | System Performance | Optimization Features | CDN integration for static assets | Standard | Not Started
FR-0208 | Cross-Phase | Performance & Optimization | System Performance | Optimization Features | Progressive loading for large lists | Standard | Not Started
FR-0209 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | Input validation and sanitization | Standard | Not Started
FR-0210 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | SQL injection prevention | Standard | Not Started
FR-0211 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | XSS protection | Standard | Not Started
FR-0212 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | CSRF tokens | Standard | Not Started
FR-0213 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | Rate limiting for API endpoints | Standard | Not Started
FR-0214 | Cross-Phase | Performance & Optimization | Security & Reliability | Security Measures | Security audit logging | Standard | Not Started
FR-0215 | Cross-Phase | Performance & Optimization | Security & Reliability | System Reliability | Error handling and recovery | Standard | Not Started
FR-0216 | Cross-Phase | Performance & Optimization | Security & Reliability | System Reliability | Transaction rollback capabilities | Standard | Not Started
FR-0217 | Cross-Phase | Performance & Optimization | Security & Reliability | System Reliability | Data backup and restore | Standard | Not Started
FR-0218 | Cross-Phase | Performance & Optimization | Security & Reliability | System Reliability | System health monitoring | Standard | Not Started
FR-0219 | Cross-Phase | Performance & Optimization | Security & Reliability | System Reliability | Automated failover mechanisms | Standard | Not Started
FR-0220 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Automated Testing | Unit tests for core business logic | Standard | Not Started
FR-0221 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Automated Testing | Integration tests for API endpoints | Standard | Not Started
FR-0222 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Automated Testing | End-to-end tests for critical workflows | Standard | Not Started
FR-0223 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Automated Testing | Performance testing for scalability | Standard | Not Started
FR-0224 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Automated Testing | Security testing for vulnerabilities | Standard | Not Started
FR-0225 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Manual Testing Procedures | User acceptance testing scenarios | Standard | Not Started
FR-0226 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Manual Testing Procedures | Cross-browser compatibility testing | Standard | Not Started
FR-0227 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Manual Testing Procedures | Mobile responsiveness testing | Standard | Not Started
FR-0228 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Manual Testing Procedures | Usability testing protocols | Standard | Not Started
FR-0229 | Cross-Phase | Testing & Quality Assurance | Testing Framework | Manual Testing Procedures | Accessibility compliance testing | Standard | Not Started
FR-0230 | Cross-Phase | Testing & Quality Assurance | Quality Standards | Code Quality | Code review procedures | Standard | Not Started
FR-0231 | Cross-Phase | Testing & Quality Assurance | Quality Standards | Code Quality | Documentation standards | Standard | Not Started
FR-0232 | Cross-Phase | Testing & Quality Assurance | Quality Standards | Code Quality | Version control workflows | Standard | Not Started
FR-0233 | Cross-Phase | Testing & Quality Assurance | Quality Standards | Code Quality | Continuous integration setup | Standard | Not Started
FR-0234 | Cross-Phase | Testing & Quality Assurance | Quality Standards | Code Quality | Deployment procedures | Standard | Not Started
FR-0235 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Multi-Device Support | Mobile-first responsive design | Standard | Not Started
FR-0236 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Multi-Device Support | Tablet optimization | Standard | Not Started
FR-0237 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Multi-Device Support | Desktop full-feature interface | Standard | Not Started
FR-0238 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Multi-Device Support | Touch-friendly controls | Standard | Not Started
FR-0239 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Multi-Device Support | Offline capability (limited features) | Standard | Not Started
FR-0240 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Mobile-Specific Features | Push notifications for alarms | Standard | Not Started
FR-0241 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Mobile-Specific Features | GPS integration for field operations | Standard | Not Started
FR-0242 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Mobile-Specific Features | Camera integration for device photos | Standard | Not Started
FR-0243 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Mobile-Specific Features | Offline device status caching | Standard | Not Started
FR-0244 | Cross-Phase | Mobile & Responsive Design | Responsive Interface | Mobile-Specific Features | Mobile app considerations | Standard | Not Started
FR-0245 | Cross-Phase | Integration & API | API Development | RESTful API | Complete CRUD operations for all entities | Standard | Not Started
FR-0246 | Cross-Phase | Integration & API | API Development | RESTful API | Authentication via JWT tokens | Standard | Not Started
FR-0247 | Cross-Phase | Integration & API | API Development | RESTful API | Rate limiting and throttling | Standard | Not Started
FR-0248 | Cross-Phase | Integration & API | API Development | RESTful API | API versioning strategy | Standard | Not Started
FR-0249 | Cross-Phase | Integration & API | API Development | RESTful API | Comprehensive API documentation | Standard | Not Started
FR-0250 | Cross-Phase | Integration & API | API Development | Real-Time Communication | WebSocket server implementation | Standard | Not Started
FR-0251 | Cross-Phase | Integration & API | API Development | Real-Time Communication | Real-time event broadcasting | Standard | Not Started
FR-0252 | Cross-Phase | Integration & API | API Development | Real-Time Communication | Connection management | Standard | Not Started
FR-0253 | Cross-Phase | Integration & API | API Development | Real-Time Communication | Message queuing for reliability | Standard | Not Started
FR-0254 | Cross-Phase | Integration & API | API Development | Real-Time Communication | Fallback mechanisms | Standard | Not Started
FR-0255 | Cross-Phase | Integration & API | Third-Party Integrations | External Services | GIS mapping services integration | Standard | Not Started
FR-0256 | Cross-Phase | Integration & API | Third-Party Integrations | External Services | Weather data APIs (for sunrise/sunset) | Standard | Not Started
FR-0257 | Cross-Phase | Integration & API | Third-Party Integrations | External Services | SMS/Email service providers | Standard | Not Started
FR-0258 | Cross-Phase | Integration & API | Third-Party Integrations | External Services | Cloud storage for file management | Standard | Not Started
FR-0259 | Cross-Phase | Integration & API | Third-Party Integrations | External Services | Monitoring and analytics services | Standard | Not Started
FR-0260 | Cross-Phase | DevOps & Deployment | Infrastructure | Deployment Pipeline | Automated CI/CD pipeline | Standard | Not Started
FR-0261 | Cross-Phase | DevOps & Deployment | Infrastructure | Deployment Pipeline | Environment separation (Dev/Staging/Prod) | Standard | Not Started
FR-0262 | Cross-Phase | DevOps & Deployment | Infrastructure | Deployment Pipeline | Database migration management | Standard | Not Started
FR-0263 | Cross-Phase | DevOps & Deployment | Infrastructure | Deployment Pipeline | Blue-green deployment strategy | Standard | Not Started
FR-0264 | Cross-Phase | DevOps & Deployment | Infrastructure | Deployment Pipeline | Rollback procedures | Standard | Not Started
FR-0265 | Cross-Phase | DevOps & Deployment | Infrastructure | Monitoring & Logging | Application performance monitoring | Standard | Not Started
FR-0266 | Cross-Phase | DevOps & Deployment | Infrastructure | Monitoring & Logging | Error tracking and alerting | Standard | Not Started
FR-0267 | Cross-Phase | DevOps & Deployment | Infrastructure | Monitoring & Logging | User activity logging | Standard | Not Started
FR-0268 | Cross-Phase | DevOps & Deployment | Infrastructure | Monitoring & Logging | System resource monitoring | Standard | Not Started
FR-0269 | Cross-Phase | DevOps & Deployment | Infrastructure | Monitoring & Logging | Log aggregation and analysis | Standard | Not Started
FR-0270 | Cross-Phase | Project Management | Documentation | Technical Documentation | API documentation (OpenAPI/Swagger) | Standard | Not Started
FR-0271 | Cross-Phase | Project Management | Documentation | Technical Documentation | Database schema documentation | Standard | Not Started
FR-0272 | Cross-Phase | Project Management | Documentation | Technical Documentation | Architecture decision records | Standard | Not Started
FR-0273 | Cross-Phase | Project Management | Documentation | Technical Documentation | Deployment guides | Standard | Not Started
FR-0274 | Cross-Phase | Project Management | Documentation | Technical Documentation | User manuals | Standard | Not Started
FR-0275 | Cross-Phase | Project Management | Documentation | Knowledge Management | Obsidian knowledge base maintenance | Standard | Not Started
FR-0276 | Cross-Phase | Project Management | Documentation | Knowledge Management | Code documentation | Standard | Not Started
FR-0277 | Cross-Phase | Project Management | Documentation | Knowledge Management | Process documentation | Standard | Not Started
FR-0278 | Cross-Phase | Project Management | Documentation | Knowledge Management | Troubleshooting guides | Standard | Not Started
FR-0279 | Cross-Phase | Project Management | Team Coordination | Development Workflow | Sprint planning procedures | Standard | Not Started
FR-0280 | Cross-Phase | Project Management | Team Coordination | Development Workflow | Code review processes | Standard | Not Started
FR-0281 | Cross-Phase | Project Management | Team Coordination | Development Workflow | Bug tracking and resolution | Standard | Not Started
FR-0282 | Cross-Phase | Project Management | Team Coordination | Development Workflow | Feature request management | Standard | Not Started
FR-0283 | Cross-Phase | Project Management | Team Coordination | Development Workflow | Release planning | Standard | Not Started

## Summary Dashboard
Metric | Value
Total Features | 283
--- BY PHASE ---
Phase 1: Core Infrastructure | 119
Phase 2: Advanced Features | 60
Phase 3: Analytics & Optimization | 19
Cross-Phase | 85
--- BY PRIORITY ---
Critical | 119
High | 60
Medium | 19
Standard | 85
--- PROJECT INFO ---
Generated Date | 2026-02-03 16:04
Project | SHUNCOM RULR IoT Platform
Company | Shanghai Shuncom AIOT Co., Ltd

## Validation Lists
Status Options | Priority Options | Test Status Options
Not Started | Critical | Not Tested
In Progress | High | Testing
Completed | Medium | Passed
Blocked | Low | Failed
On Hold | Standard | Skipped
Under Review